## Sheet1
Test Case ID | Test Scenario | Test Steps | Test Data | Expected Results | Actual Results | Status (Pass/Fail) | Test Comments | Hours
QBRW1 | Establish Google Calendar integration with Bookings module | Step1- Open Booking Module | Testing Data | validation should be perform on booking form.(updation also) | Form submitted | Fail | Work on date & time validation. | 3
| Enable the creation of follow-up events or activities (i.e. phone call, email, and meeting) for a particular lead. Lead will be looked up automatically from within Calendar event. | Step1 - add activity | Testing Data | Activity Should be Shows on google calender | Activity Does not show on google Calender | Fail | Work to show activity on google calender | 16
| Enable Team member or specific team assignment or reassignment to a particular event and/or activity | Step-1 Assign member to activity and reassign also | Testing Data | Team Member assign and reassign Successfully | As expected | Pass
| Assure there are no booking conflicts that arise | Step1- Open Booking Module | Testing Data | Time validation should be perform on booking form.(updation also) | Time Validation not perform while booking Form | Fail | Work on time validation | 2
| Assure a Team Calendar view is operational | Step1 - Open Booking Module | Testing Data | Calendar view is operational | Calendar view is operational | pass
| Apply a more appealing aesthetic look like Google Calendar | [5 empty] | calender will look good when we change text-size,color,background-color | Already added time in calendar module
QBRW2 | Establish the creation of follow-up events or activities (i.e. phone call, email, meeting) | Step-1 Create Activity | Testing Data | Email should be sent on followup events or activities ,phone call and meeting shows on calender. | Email is not sending. | Fail |  | Already added time in calendar module
| Enable two-way email sync | Step-1 Send Mail and Reply to that Send mail | Testing Data | two-way email sync | Reply is not showing on dashboard | Fail | Work on two-way email sync | 24
| Resolve email attachments issue | Step-1 Click on Send Email button from lead module | Testing Data | Attachment is shown on email template editor | Attachment button is not showing on email template editor | Fail | Work on Email Attachment Button | 8
| Establish email tracking notifications issue opened, clicked or bounced, when and how many times. The tracked emails must appear in the activity stream of the lead record’s page |  |  | Email Tracking Notifications issue opened and tracking email show on lead record page | popup is not showing and email is also not showing on lead record page | Fail | Is this primary function you want ?
| Enabling click-to-call integration (i.e. Dialing out/receiving calls) with Ring Central VOIP provider. | Step 1:Click on reports and then click on dial out calls | Testing Data | VOIP service is not integrated | Link is not working | Fail
| Enable forwarding, on hold, conferencing and other useful features | Step 1:Click on reports and then click on dial out calls | Testing Data | VOIP service is not integrated | Link is not working | Fail
| Automatically Logging history of calls within Lead | Step1:Click on Lead | Testing Data | VOIP service is not integrated | Logging history is not showing in lead | Fail | work on history of calls
| Establish multiple “Qualifying” campaigns so that multiple surveys should be permissible for each Lead |  |  | Query | Query |  | Please explain
QBRW3
QBRW4 | Resolve email embedded video issue | Step 1:Click On Email template | Testing Data | Shows email embedded video | Shows email embedded video | Pass
QBRW5 | Client Module
| Assure that email templates appear correctly on Desktop and Android devices | Step 1:Click On Email template | Testing Data | New Email template is shows good on android device but all Email template View is not responsive | all Email template view is not responsive | Fail | work on responsiveness | 2
| Enable cloning of templates | Step 1:Click On Email template | Testing Data | Cloning of templates work | Cloning of template is not working | Fail | enable option of cloning template | 8
QBRW4
| Payrroll Module | Step 1:Click On Payroll | Testing Data | Activate users and deactivate users | Activation and deactivation of users is not working | Fail | Work on bulk action | 12
Step 2:Click on bulk action
QBRW5 | Report Module | Step 1:Click On Report Module | Testing Data | Dial out calls link is working | Dial out calls link is not working(feature not available) | Fail | VOIP service is not integrated
|  | Step 2:Click On Report Module | Testing Data | Contractor / Payroll hours link is working | Contractor / Payroll hours link is not working(feature not available) | Fail | Please explain this functionality
Total Time:75 hours
| Change password function |  |  | Change password function not working |  | Fail |  | 4
| Create a visual display of the Sales Pipeline and accurate timeline for each phase | [6 empty] | 32
| Assure stats are operating and reporting correctly | [6 empty] | 2
| Assure targets can be defined | [6 empty] | 2
| Assure hot leads are reported | [6 empty] | 2
| Assure workflow automation is operating with proper email notifications according to Sales Pipeline design | [6 empty] | 2